## Cover
Summary:
Gantt Chart
Document Description:
Gantt Chart is bar chart of schedule information where
activities are listed on the vertical axis, dates are shown
on the horizontal axis, and activity durations are shown
as horizontal bars placed according to start and finish dates.
Project:
R.A.D.U. - Requirements And Design Utility
Author | Function/Department | Date | Signature
Madalina Fantana |  | 2019-07-10
Approved by | Function/Department | Date | Signature
NTT Data Romania S.A.
19-21, Constanta Street,
400158 Cluj Napoca

## Requirements
Project Planner
R.A.D.U - REQUIREMENTS AND DESIGN UTILITY |  |  |  |  | Period Highlight: |  | 9 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | RESPONSIBLE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Req001 | 2 |  | 2 |  | 100% | Iulia
Req002 | 2 |  | 2 |  | 100% | Iulia
Req003 | 9 |  | 9 |  | 0% | Iulia
Req004 | 2 |  | 2 |  | 100% | Iulia
Req005 | 2 |  | 2 |  | 100% | Iulia
Req006 | 2 |  | 2 |  | 100% | Iulia
Req007 | 2 |  | 2 |  | 100% | Iulia
Req008 | 2 |  | 2 |  | 100% | Iulia
Req009 | 2 |  | 2 |  | 100% | Iulia
Req010 | 2 |  | 2 |  | 100% | Iulia
Req011 | 2 |  | 2 |  | 100% | Iulia
Req012 | 2 |  | 2 |  | 100% | Iulia
Req013 | 2 |  | 2 |  | 100% | Iulia
Req014 | 2 |  | 2 |  | 100% | Iulia
Req015 | 2 |  | 2 |  | 100% | Iulia
Req016 | 2 |  | 2 |  | 100% | Iulia
Req017 | 2 |  | 2 |  | 100% | Iulia
Req018 | 2 |  | 2 |  | 100% | Iulia
Req019 | 2 |  | 2 |  | 100% | Iulia
Req020 | 2 |  | 2 |  | 100% | Iulia
Req021 | 2 |  | 2 |  | 100% | Iulia
Req022 | 2 |  | 2 |  | 100% | Iulia
Req023 | 2 |  | 2 |  | 100% | Iulia
Req024 | 2 |  | 2 |  | 100% | Iulia
Req025 | 2 |  | 2 |  | 100% | Iulia
Req026 | 2 |  | 2 |  | 100% | Iulia
Req027 | 2 |  | 2 |  | 100% | Iulia
Req028 | 2 |  | 2 |  | 100% | Iulia
Req029 | 2 |  | 2 |  | 100% | Iulia
Req030 | 2 |  | 2 |  | 100% | Iulia
Req031 | 2 |  | 2 |  | 100% | Iulia
Req032 | 2 |  | 2 |  | 100% | Iulia
Req033 | 2 |  | 2 |  | 100% | Iulia
Req034 | 2 |  | 2 |  | 100% | Iulia
Req035 | 2 |  | 2 |  | 100% | Iulia
Req036 | 2 |  | 2 |  | 100% | Iulia
Req037 | 2 |  | 2 |  | 100% | Iulia
Req038 | 2 |  | 2 |  | 100% | Iulia
Req039 | 2 |  | 2 |  | 100% | Iulia
Req040 | 5 |  | 5 |  | 80%
Req041 | 5 |  | 5 |  | 80%
Req042 | 5 |  | 5 |  | 80%
Req043 | 5 |  | 5 |  | 80%
Req044 | 5 |  | 5 |  | 80%
Req045 | 5 |  | 5 |  | 80%
Req046 | 9 |  | 9 |  | 0%
Req047 | 2 |  | 2 |  | 100% | Iulia
Req048 | 2 |  | 2 |  | 90% | Catalin
Req049 | 2 |  | 2 |  | 100% | Iulia
Req050 | 5 |  | 5 |  | 100% | Rares
Req051 | 5 |  | 5 |  | 100%
Req052 | 5 |  | 5 |  | 100%
Req053 | 2 |  | 2 |  | 100% | Catalin
Req054 | 2 |  | 2 |  | 100% | Catalin
Req055 | 2 |  | 2 |  | 100% | Catalin
Req056 | 2 |  | 2 |  | 100% | Catalin
Req057 | 2 |  | 2 |  | 100%
Req058 | 9 |  | 9 |  | 0%
Req059 | 2 |  | 2 |  | 100%
Req060 | 2 |  | 2 |  | 100%
Req061 | 2 |  | 2 |  | 100%
Req062 | 2 |  | 2 |  | 100%
Req063 | 2 |  | 2 |  | 100%
Req064 | 2 |  | 2 |  | 100% | Rares
Req065 | 2 |  | 2 |  | 100% | Rares
Req066 | 2 |  | 2 |  | 100%
Req067 | 2 |  | 2 |  | 100% | Rares
Req068 | 2 |  | 2 |  | 100% | Rares
Req069 | 2 |  | 2 |  | 80% | Rares
Req070 | 2 |  | 2 |  | 0%
Req071 | 9 |  | 9 |  | 0%
Req072 | 9 |  | 9 |  | 0%
Req073 | 9 |  | 9 |  | 0%
Req074 | 2 |  | 2 |  | 100%
Req075 | 6 |  | 6 |  | 33%
Req076 | 2 |  | 2 |  | 100%
Req077 | 2 |  | 2 |  | 100%
Req078 | 2 |  | 2 |  | 100%
Req079 | 2 |  | 2 |  | 100%
Req080 | 2 |  | 2 |  | 100% | Rares
Req081 | 9 |  | 9 |  | 0%
Req082 | 2 |  | 2 |  | 100%
Req083 | 2 |  | 2 |  | 100%
Req100 | 9 |  | 9 |  | 0%
Req101 | 9 |  | 9 |  | 0%
Req102 | 9 |  | 9 |  | 0%